## Slide 2
Plan for pipeline Development/Testing/Sign-off and Go Live (Application wise)
 | Line Items | Pipeline count | Start Date | ETA | Status | POC | Risks / Dependency
Phase 1 | Abb.com (Jenkins) and Redirection-proxy-config | 26 | 26-Jul | 26-Sep | Completed |  | 
 | InsidePlus | 1 | 26-Jul | 26-Sep | Docker Issue | Arek | Arek to sync with ABB ADO team for ACR setup
 | NewsBank | 2 | 26-Jul | 26-Sep | Completed | Abhishek | 
 | Assigned to QA | 28 | 29-Sep | 14-Oct | Completed |  | 
 | Sign-off for readiness for Go-Live (from ABB) |  | 25-Oct | 28-Oct | Completed ( for 28) |  | Ready for Go live
 | Go Live |  | NA | 10-Dec | Pending for Sign Off ABB and QA | Sylwia, Bartlo, Arek | 
Phase 2 | InsidePlus | 9 |  |  |  |  | 
 | InsidePlus Development | 9 | 27-Sep | 7-Oct | Completed | Pallavi | 
 | Assigned to QA | 9 | 17-Oct | 31-Oct | completed | Greg | received Dev-Ops Sign off
 | Sign-off for readiness for Go-Live (from ABB) |  | 24-Oct 18-Nov | 28-Oct 24-Nov | Stage testing approved by Dev Ops | Sylwia , Bartlo, Arkadiusz | Go Live Done
 | NewsBank | 10 |  |  |  |  | 
 | News Bank Set 1 Development | 10 | 10-Oct | 14-Oct | Completed | Pallavi, Abhishek | 
 | QA assignment | 10 | 31-Oct 7-Novv | 25-Nov | Completed | Ehsan Ahmad | 

## Slide 3
Plan for pipeline Development/Testing/Sign-off and Go Live (Application wise)
 | Line Items | Pipeline count | Start Date | ETA | Status | POC | Risks / Dependency
Phase2 | WAT |  | 14-Oct | 28-Oct |  |  | 
 | WAT Development | 15 | 17-Oct | 11-Nov | WIP | Pallavi , Abhishek | 
 | WAT Sprint 1 | 7 | 17-Oct 07-Nov 26 Dec | 31-Oct 18 Nov 30-Dec | WIP | Pallavi , Abhishek, Arek | 
 | WAT Sprint 2 | 8 | 07-Nov 12-Dec 26 Dec | 18-Nov 16-Dec 30-Dec |  | Pallavi , Abhishek | Till now we have got success in completing till stage for 14 pipelines.
 | Assigned to QA |  | 05-Nov 19-Dec 27 Dec | 22-Nov 23-Dec 30 Dec | Post Development | Sprint wise assignment to QA Team | 
 | Sign-off for readiness for Go-Live (from ABB) |  | 22-Nov 26 Dec 02 Jan 23 | 14-Nov 30 Dec 06 Jan 23 |  |  | 
WAT application has very complex logic and breaking into modules is taking a lot of efforts.
There is loss of time in undersetting the configurations, due to complexity and knowledge gap within app and ops team.
This is resulting in redeveloping the entire logic for multiple stages due to introduction of new requirement of redeveloping the on-cloud server. We are working with ABB Dev-Ops team to set up two self hosted agents in cloud.
Till now we have got success in -
Started migration from onprem to cloud
Assisting cloud team for setup of onprem servers to Self hosted cloud server
Received partial KT from Testing team about the flow of selenium testing in Jenkins pipeline
9 stages pipeline development completed for WAT out of 15

## Slide 4
Plan for pipeline Development/Testing/Sign-off and Go Live (Application wise)
 | Line Items | Pipeline count | Start Date | ETA | Status | POC | Risks / Dependency
Phase2 | ABB.COM (6) and FIFA (1) |  | 31-Oct | 11-Nov |  |  | 
 | ABB.COM Development | 7 | 14-Nov | 25-Nov | WIP (1/7) | Pallavi, Abhishek | Pending for app team availability to fix the issue together
 | Assigned to QA |  | 28-Nov | 30-Nov | 6/7 assigned to QA |  | 
 | Sign-off for readiness for Go-Live (from ABB) |  | 30-Nov | 2-Dec | Post QA sign off |  | 
 | NewsBank |  | 14-Nov | 25-Nov |  |  | 
 | NewsBank Set 2 Development | 19 |  |  | 19 Completed |  | 
 | Assigned to QA -29 Pipelines (Set1, Set2) |  | 28-Nov 07-Nov | 25-Nov | Assigned to QA Team | Ehsan | 
 | Sign-off for readiness for Go-Live (from ABB) |  | 22-Nov | 05-Dec | Completed |  | Go Live done on 21 Dec 23
 | Overall GoLive- InsidePlus, WAT, ABB.COM, NewsBank |  | 30-Nov | 19-Dec | ABB.com go live to be planned |  | News bank and Inside Plus Go live done
 | Transition and Hyper Care- 3 Weeks |  | 19-Dec-22 | 06-Jan-23 |  |  | 

## Slide 5
Project status overview
Recent achievements (19th Dec – 23rd Dec)
Next steps (26th Dec – 30th Dec)
Overall project status]
Scope
Time
Budget
Phase-1
No Go live date with new pipelines
Phase-2
News Bank QA sign off and Go live support
WAT environment readiness support to Dev-Ops team
Inside + Docker Issue (WIP) – worked with Arek
and the pipeline is given for testing by commenting the quality stage as the docker is yet to be set up.
Rewriting of WAT pipelines logic
WAT pipeline re development
WAT pipeline testing
News bank hyper Care
ABB.com QA support
Delays are observed for below reasons
  env availability for WAT development and testing
  Understanding the WAT application logic and config due to multiple dependencies on apps team and access relates issues
  Rewriting of the logic due to cloud agent approach and then on prim agent approach in WAT
  ABB.com Go live not finalized
This is impacting the schedule , efforts and cost of the project now

## Slide 6: Pipeline Count Tracking
Status | Abb.com | Inside+ | News Bank | WAT | Total
Pending with Project Team | 1 | 1 | 0 | 15 | 17
Pending for Application Team sign Off (QA Sign Off) | 6 | 0 | 0 | 0 | 6
Pending with Dev-Ops Team for UAT sign off | 0 | 0 | 0 | 0 | 0
UAT Complete (Dev-Ops Sign Off) | 24 | 0 | 0 | 0 | 24
Go Live done | 2 | 9 | 31 | 0 | 42
Grand Total | 33 | 10 | 31 | 15 | 89
  Summary :
  Phase 1: 2/29 - Go Live Completed
  24/29 – Received UAT approval – No Go live confirmation
  Phase 2:
  Inside+ :: 9 – Go live done on 10 Dec ; News Bank 31 pipelines Go live done on 21 Dec 22
  For ABB.com, requesting ABB team to provide tentative Go Live date.
  WAT :: 15 WIP – For 14 pipelines 6 stages are again getting re-developed. At present stuck with self hosted agent.

## Slide 7: Risks
S.No. | Risks | Mitigation / issue details | Owner | Deliverable Impacted | Reported Date | Priority | Resolved Date | Status
1 | Holiday / Planned Leaves of ABB team | The ABB team must keep Dev team informed about their availability for testing / sign off | ABB | Transition and Deployment | NA | High | NA | Sylwia confirmed to provide sign off before Mid Dec
2 | Go Live of Phase 1 – 28 pipelines is delayed | ABB to help in getting UAT approval and get Go Live scheduled for ABB.com and Inside+ by 25th Nov 2022 also provide the go live date from Dev-Ops Team. | ABB | Go Live and Hypercare | 18 Nov 22 | Critical |  | Go Live postponed
3 | WAT Application Pipeline Development is delayed | The issues are showing up in each stage. there are 15 stages in one pipeline and 6 stages are done as of now , the issues are reported on priority to ABB, and must be given priority to fix them | ABB | WAT Development | 14 Nov 22 | High |  | The pipelines are getting redeveloped hence taking time as the existing logic can not be migrated as is to Azure pipelines
4 | WAT Go Live Overlapping with Production Freeze Time | ABB team to help in getting exception approval for go live in Freezing time | ABB | WAT Go Live | 05 Dec 22 | High |  | 

## Slide 8: Issues
S.No. | Issue Description | Mitigation / issue details | Owner | Deliverable Impacted | Reported Date | Resolved Date | Status
1 | Self-hosted Agent Permission Issue | To take Areks Help | ABB | WAT Development | 08 Nov 22 | 14 Nov 22 | Completed
2 | No-Space-Left issue in server | Escalated to Dev Ops Team | ABB | WAT Development | 15 Nov 22 | 18 Nov 22 | Completed
3 | Server Down Issue | Escalated to Dev Ops Team | ABB | WAT development | 16 Nov 22 | 17 Nov 22 | Issue Fixed but the data lost so team is redeveloping the pipeline
4 | pl-s-devserv3.pl.abb.com pl-s-insreg04.pl.abb.com Access request | To take Areks Help | ABB | WAT Development | 15 Nov 22 | 18 Nov 22 | Completed
5 | ABB.com Phase 2 FIFA branch creation got stuck | Escalated to Arek for guidance on access request | ABB | Abb.com Phase 2 | 17 Nov 22 | 22 Nov 22 | Resolved
6 | News Bank (NB) Phase 2 – 5 pipelines pending for completion with application Team | Application Team to provide half a day to project team to execute two steps together | NB App Team | NB phase 2 | 22 Nov 22 | 05 Dec 22 | Completed
7 | ABB.com Redirection pipelines are failing in Prod | To get Areks help to identify access / config issue To take Business Approval for prod testing | ABB | ABB.com UAT | 24 Nov 22 | 28 Nov 22 | Go live done

## Slide 9: Issues
S.No. | Issue Description | Mitigation / issue details | Owner | Deliverable Impacted | Reported Date | Resolved Date | Status
8 | WAT Application – Connectivity issue between ADO and DB Server As discussed with Arek , the development should be done in such a way we should be able to connect to DB in AWS in future. | 1. To do this additional development additional time is required. 2. Availability of Microsoft support or Azure DB team is required if present in ABB 3. To at least test the pipelines workability we require access to existing on prim servers | ABB | WAT Development | 28 Nov 22 | 30 Nov 22 | Completed
9 | Nuget Package Push Request for WAT Application | Arek to Push the packages | ABB | WAT Development | 5 Dec 22 | 6 Dec 22 | Completed
10 | Jenkins Agent availability and upgrade | Reported to Arek for Jenkins issues and requested upgrade | ABB | WAT Development | 06 Dec 22 | 08 Dec 22 | Completed
11 | Testing framework Clarity in WAT application | Working with ABB dev ops team to get the details of selenium configuration. As the dev ops team is engaged in Jenkins issue the availability to work together is limited | ABB | WAT Development | 07 Dec 22 |  | WIP

## Slide 10: Issues
S.No. | Issue Description | Mitigation / issue details | Owner | Deliverable Impacted | Reported Date | Resolved Date | Status
12 | Jenkins Self hosted agent for WAT application is not available | Dev team is using other servers self hosted agent, but it is giving errors, while Arek is working on getting WAT application agent work. | ABB | WAT Development | 09 Dec 22 |  | WIP
13 | Jenkins Autowfe server down | Dev-Ops team and Arek to help fixing the issue | ABB | WAT Development | 09 Dec 22 |  | WIP
14 | Peer's Certificate issue in WordPress for data generation stage | Dev-Ops team is working on these issues | ABB | WAT Development | 08 Dec 22 | 13 Dec 22 | Fixed by project team
15 | Configuration of Smoke-API and Regression Testing and selenium tool in the cloud VM | Dev-Ops team is working on these issues | ABB | WAT Development | 08 Dec 22 |  | WIP
16 | Wp file path issue for template-tests stage | Dev-Ops team is working on these issues | ABB | WAT Development | 09 Dec 22 | 20 Dec 22 | Completed
17 | Plugin Activation issue in data generation stage | App team to validate the data and share observations based on that WAT application team to correct the data | ABB | WAT Development | 12 Dec 22 | 20 Dec 22 | Completed

## Slide 11: Issues
S.No. | Issue Description | Mitigation / issue details | Owner | Deliverable Impacted | Reported Date | Resolved Date | Status
18 | Azure container registry setup | Arek to sync with ABB ADO team for ACR setup | ABB | WAT Development | 14 Dec 22 |  | WIP
19 | ABB.com Go Live got dragged | Application team to plan the Go live and approve the pull requests in the pipelines | ABB.com app team and Akash Gautam | Go live of Abb.com | 08 Nov 22 |  | 
20 | News bank Go Live delayed | News Bank app team and dev ops team provide sign off on priority and confirm Go Live date | NB app team | Go live News Bank | 14 Dec 22 | 21 Dec 22 | Completed
21 | ABB.com search pipeline is stuck at source path missing issue | Escalated to application team leads Ivan and Akash to help resolving path , still waiting for application team availability | ABB / Abb.com app team | Abb.com phase 2 development | 02 Dec 22 |  | WIP